EduRAG — Sprint 4 Plan

Project 37  |  Group 19  |  CSIT321  |  University of Wollongong

Sprint Dates: 29 April – 13 May 2026

# Sprint Goal

Submit Assessment 2 (due 8 May), close all remaining Sprint 3 gaps, stand up the first connected Streamlit to Flask API prototype, and deliver the interface design assets required for Assessment 3 (due 29 May) — so Sprint 5 can begin feature implementation with no outstanding design or documentation debt.

# Hard Deadlines This Sprint

| Date | Event | Notes |
| --- | --- | --- |
| Fri 8 May, 11 pm | Assessment 2 — Moodle Submission Deadline | Tai (submission owner). All blockers resolved by Thu 7 May. |
| Wed 13 May | Sprint 4 Retrospective and Sprint 5 Kickoff | All team |
| Fri 29 May | Assessment 3 — Presentation + PDF + Video (8 min) | Sprint 4 prototype and demo screenshots are the A3 interactive demo evidence |

# Task Assignments

Bold = CRITICAL task. Italic = Stretch task (attempt only after all other owner tasks are complete). Tick ☐ when done.

| # | Task | Deadline | Expected Output | Notes / Dependencies | Done |
| --- | --- | --- | --- | --- | --- |
| Thanh Binh Tran — Project Lead / RAG Backend |  |  |  |  |  |
| 1 | Fix A2 Appendix G and final proofread | Tue 5 May | Assessment_2_Group19_final.pdf ready for upload | Two-person review with Tai before handoff to Task 21 | ☐ |
| 2 | Flask API wrapper — 5 core endpoints | Sun 10 May | src/api/app.py + src/api/routes/ | Pre-req for Tasks 6, 15, 19, 22. Must land Sun 10 to protect Mon 11 chain. | ☐ |
| 3 | Rerun RAG benchmark against 31-query corpus | Tue 12 May | Updated docs/rag_config.md + docs/rag_config_benchmark_31q.json | Needs Task 15 first | ☐ |
| 4 | File PoC recording link in demo document | Thu 7 May | Recording link committed to sprint3_internal_demo.md | Closes Sprint 3 Task 6 partial gap | ☐ |
| 5 | Sprint 5 plan outline | Tue 12 May | docs/sprint_5_kickoff.md | Drafted during retrospective prep | ☐ |
| Anmoldeep Singh — UI / Frontend |  |  |  |  |  |
| 6 | Wire Streamlit to Flask API | Mon 11 May | app/main.py with real HTTP calls + README_app.md | Needs Task 2. Use fixture JSON fallback if Task 2 slips to Mon 11. | ☐ |
| 7 | Finalize branding | Tue 5 May | Updated docs/design_system.md; Streamlit app visually consistent | Group name, logo, colours locked for A2 and all future submissions | ☐ |
| 8 | A3 interface demo screenshots | Tue 12 May | docs/a3_interface_demo/ — 6 annotated PNGs + narrative.md | Needs Task 6. These are the A3 interactive demo evidence. | ☐ |
| 9 | React scaffold (stretch) | Tue 12 May | frontend/ — Vite + React + Tailwind skeleton wired to Flask API | Only if Tasks 6, 7, 8 done. Not required for A3. | ☐ |
| Thi Hong Ngoc Nguyen — RAG Internals |  |  |  |  |  |
| 10 | embedder.py standalone module + benchmarks | Thu 7 May | src/vector_retriever/embedder.py + docs/embedding_benchmarks.md | Closes Sprint 3 Task 15 partial gap | ☐ |
| 11 | PPTX and DOCX chunker extension | Sun 10 May | Updated chunker.py with PPTX + DOCX paths; pytest passing | Pre-req for Tasks 12 and 16 | ☐ |
| 12 | Parser evaluation update — PPTX and DOCX results | Mon 11 May | Updated docs/parser_evaluation.md with multi-format comparison matrix | Needs Task 11 | ☐ |
| Tung Phuong Anh Huynh — Coordination / Testing |  |  |  |  |  |
| 13 | Write sprint3_sponsor_review.docx | Mon 4 May | docs/meetings/sprint3_sponsor_review.docx merged to develop | CRITICAL — only hard-missing Sprint 3 deliverable. Source: Wrapup.md Section 2. | ☐ |
| 14 | Complete sprint3 meeting report set | Wed 6 May | All missing docs/meetings/sprint3_*.docx filed | Must be done before Task 21 | ☐ |
| 15 | Run 31-query test against Flask API | Mon 11 May | docs/test_results_sprint4.md — per-query result table | Needs Task 2. Feeds Task 3. | ☐ |
| 16 | Sample corpus expansion — 3 or more new docs | Mon 11 May | Updated sample_manifest.md; confirmed loading through PPTX/DOCX chunker | Needs Task 11 | ☐ |
| 17 | Sprint 4 sponsor meeting with Prof. Yan | Tue 12 May | docs/meetings/sprint4_sponsor_review.docx | Schedule after Task 6 is working — show live prototype | ☐ |
| Kahavidanage Namaratne — Architecture / Data |  |  |  |  |  |
| 18 | ERD v2 final — reconcile against live SQL schema | Sun 10 May | docs/architecture/erd_v2.png + docs/erd_v2_changes.md | Cross-check against 001_initial_schema.sql (already complete) | ☐ |
| 19 | Flask API query sequence diagram | Mon 11 May | docs/architecture/seq_api_query.png | Needs Task 2 — diagram real Flask routes, not design fiction | ☐ |
| 20 | Sprint 4 risk register update | Tue 12 May | Updated docs/risk_register.md | — | ☐ |
| Tai Huynh — Ethics / Documentation |  |  |  |  |  |
| 21 | A2 final review and Moodle submission | Fri 8 May | Confirmed Moodle submission receipt by 11 pm | HARD DEADLINE — needs Tasks 1, 13, 14 complete first | ☐ |
| 22 | Update api_spec.yaml against Flask routes | Mon 11 May | Re-validated docs/api/api_spec.yaml (OpenAPI 3.0.3) | Needs Task 2 | ☐ |
| 23 | A3 document first draft | Tue 12 May | docs/a3_draft.docx — design methodology + requirements + interface section (max 2000 words) | Needs Tasks 6 and 8 | ☐ |
| 24 | Sprint 4 summary document | Wed 13 May | docs/sprint4_summary.md | Retrospective day deliverable | ☐ |

# A2 Report Enrichment Add-On Tasks

All five A2 enrichment items are due by Wed 6 May 2026, leaving Thu 7 May as the final integration and re-export buffer before the Fri 8 May Moodle deadline.

| # | Owner | Deadline | A2 Enrichment Task | Expected Output / Notes | Done |
| --- | --- | --- | --- | --- | --- |
| 25 | Anmoldeep Singh | Tue 5 May | A2 acceptance criteria and validation plan | Acceptance criteria table for FR/NFR groups. Cover citations, confidence indicator, course selection, upload/indexing status, role navigation, fallback label, accessibility, and colour consistency. | ☐ |
| 26 | Thanh Binh Tran | Tue 5 May | Project difficulty justification matrix | 0.5-page difficulty matrix for Creativity/Innovation. Cover hallucination control, retrieval quality, multi-role access, persistence, document parsing, and auditability. | ☐ |
| 27 | Kahavidanage Namaratne | Wed 6 May | A2 technical risk matrix | A2-focused risk register excerpt. Include RAG quality, privacy, upload/indexing, latency, RBAC, PDF/export, and mitigation owners. | ☐ |
| 28 | Tung Phuong Anh Huynh | Wed 6 May | Supervisor consultation evidence map | Consultation-to-requirement decision table using sponsor/review notes. Show scope decisions without inventing meeting evidence. | ☐ |
| 29 | Thi Hong Ngoc Nguyen | Wed 6 May | RAG evaluation strategy | Short evaluation plan with sample questions and metrics: groundedness, citation accuracy, retrieval relevance, fallback correctness, latency, and course-isolation checks. | ☐ |
| 30 | Tai Huynh + Thanh Binh Tran | Wed 6 May | Market Analysis and Project Rationale | Market Context, Student Problem, AI Adoption trend, Trust and Accuracy Gap, Target users, Why Paedia is needed, Competitive positioning. Must include real figures for clear evidence. | ☐ |

# Sprint 4 Milestones

| Date | Milestone | Owner(s) | Status |
| --- | --- | --- | --- |
| Mon 4 May | Task 13 merged to develop — sprint3_sponsor_review.docx | Tung | Planned |
| Tue 5 May | Tasks 1 and 7 done — A2 Appendix G fixed; branding finalized | Binh, Anmoldeep | Planned |
| Wed 6 May | Task 14 done — full Sprint 3 meeting report set filed | Tung | Planned |
| Thu 7 May | Tasks 4 and 10 done — recording link filed; embedder.py merged | Binh, Ngoc | Planned |
| Fri 8 May | Task 21 — Assessment 2 submitted to Moodle by 11 pm | Tai (all support) | HARD DL |
| Sun 10 May | Tasks 2, 11, 18 done — Flask API, PPTX/DOCX chunker, ERD v2 ready | Binh, Ngoc, Namaratne | Planned |
| Mon 11 May | Tasks 6, 12, 15, 16, 19, 22 done — Streamlit wired; downstream clear | All | Planned |
| Tue 12 May | Tasks 3, 5, 8, 17, 20, 23 done — demo screenshots, A3 draft, sponsor meeting | All | Planned |
| Wed 13 May | Task 24 done — Sprint 4 summary and retrospective | Tai + All | Planned |

# Critical Path

Buffer logic: Tasks 2 and 11 are due Sunday 10 May so downstream tasks (Mon 11) have a full day of buffer if either slips over the weekend. Task 13 is due Monday 4 May to give Tai four days of review before the Friday 8 May deadline.

| Chain | Dependency Sequence |
| --- | --- |
| Chain A — A2 Submission | Task 13 (sponsor docx, Mon 4) → Task 1 (A2 fix, Tue 5) → Task 14 (meeting reports, Wed 6) → Task 21 (Moodle submit, Fri 8 May) |
| Chain B — Prototype Build | Task 2 (Flask API, Sun 10) → Task 6 (Streamlit wire, Mon 11) → Task 8 (demo screenshots, Tue 12) → Task 23 (A3 draft) |
| Chain C — Testing & Benchmarking | Task 2 (Flask API) → Task 15 (31-query test, Mon 11) → Task 3 (benchmark update, Tue 12) |
| Chain D — Multi-format Support | Task 11 (PPTX/DOCX chunker, Sun 10) → Tasks 12 + 16 (parser eval + corpus expansion, Mon 11) |

# Sprint 4 Risks

| Risk | Impact if Realised | Mitigation |
| --- | --- | --- |
| Flask API (Task 2) slips past Sun 10 May | Blocks Tasks 6, 15, 19, 22 — cascades to A3 demo and A3 draft | Binh starts Task 2 on day one. Task 6 uses fixture JSON fallback until API is ready. |
| Task 13 sponsor docx cannot be reconstructed accurately | Sprint 3 hard-missing gap stays open; A2 content completeness weakened | Use EduRAG_Project_Wrapup.md Section 2 (15 Apr meeting notes) as canonical source. |
| A3 video production underestimated | A3 (29 May) delivered with unpolished demo footage | Sprint 4 captures screenshots and screen recording. A3 video editing is Sprint 5 work. |
| A2 Appendix G fix introduces new formatting errors | PDF corrupted before submission | Two-person review (Binh + Tai) of the exported PDF before upload. |
| PPTX/DOCX chunker (Task 11) exposes parsing edge cases | Corpus expansion (Task 16) blocked or fails silently | Ngoc targets standard layouts first. Edge cases documented for Sprint 5. |

# Sprint 4 Timeline — Gantt Chart

30 April – 13 May 2026  |  Tasks 1–30  |  Bold name = critical  |  Italic name = stretch

| # | Task | Owner | A30 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Fix A2 Appendix G | Binh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Flask API wrapper | Binh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | RAG benchmark rerun | Binh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | File PoC recording link | Binh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Sprint 5 plan outline | Binh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Wire Streamlit to Flask API | Anmoldeep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Finalize branding | Anmoldeep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | A3 interface demo screenshots | Anmoldeep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | React scaffold (stretch) | Anmoldeep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | embedder.py + benchmarks | Ngoc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | PPTX/DOCX chunker | Ngoc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Parser evaluation update | Ngoc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | sprint3_sponsor_review.docx | Tung |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | sprint3 meeting report set | Tung |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 | 31-query API test | Tung |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 | Corpus expansion | Tung |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 | Sprint 4 sponsor meeting | Tung |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 | ERD v2 final | Namaratne |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 | Flask API seq diagram | Namaratne |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 20 | Risk register update | Namaratne |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21 | A2 final review + submit | Tai |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 22 | Update api_spec.yaml | Tai |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 23 | A3 document first draft | Tai |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24 | Sprint 4 summary | Tai |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25 | A2 acceptance criteria | Anmoldeep |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 26 | Difficulty matrix | Binh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 27 | A2 technical risk matrix | Namaratne |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 28 | Consultation evidence map | Tung |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 29 | RAG evaluation strategy | Ngoc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 30 | Market Analysis | Tai+Binh |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# Legend

Dark blue cell = task active  |  Red column = A2 deadline day (8 May)  |  Bold task name = CRITICAL  |  Italic task name = stretch